## Issues Fixed
# | Application / URL | Steps (summary) | Reported Issue | Root Cause | Fix Applied | Status
1 | OrangeHRM demo (dashboard / login) | Create project -> select module -> AI generate -> Run automation | timeout: Timed out receiving message from renderer (Chrome) | Page-load waited for all network/resources; Chrome renderer hung; no retry | pageLoadStrategy=eager; stability flags; page load 90s; navigate() retries + soft continue; restart browser once | FIXED
2 | ParaBank Online Banking | Scan Application | Scan failed / renderer or page-load error | Same renderer page-load timeout during Scan navigation | Same browser harden + discovery uses navigate() and accepts interactive readyState | FIXED
3 | https://practice.expandtesting.com/login | New Project -> Scan Application | timeout: Timed out receiving message from renderer (Edge) | Edge had weaker options than Chrome; same renderer timeout | Edge now uses same stability args + eager strategy + retries | FIXED
4 | https://phptravels.net/admin | New Project -> Scan Application | timeout: Timed out receiving message from renderer (Edge) | Same as #3 | Same Edge/Chrome harden path | FIXED
5 | https://opensource-demo.orangehrmlive.com/.../auth/login | New Project -> Scan Application | timeout: Timed out receiving message from renderer (Edge) | Same as #3 | Same Edge/Chrome harden path | FIXED
6 | https://www.saucedemo.com/inventory.html | Login flow / Open Menu verify | timeout: Timed out receiving message from renderer (Chrome) | Same Chrome renderer timeout on navigate | navigate() used in runner + session reset; generated scripts also hardened | FIXED

## Dev Notes
Item | Detail
Build | UTS-Test-Automation-Suite (renderer-timeout fix release)
Key files | automation/selenium_session.py, config/selenium.json, dynamic/discovery.py, dynamic/automation_runner.py, automation/session_reset.py, selenium_script_generator.py
Config defaults | page_load_strategy=eager; page_load_timeout_seconds=90; script_timeout_seconds=60; navigation_retries=3
How to verify | 1) SETUP.bat 2) RUN-WEB.bat 3) Recreate each project from Issues.xlsx 4) Scan Application / Run automation
Browser tip | Prefer Chrome. If Edge still flaky, switch project Browser to Chrome.
Not a product bug | Target site outage / captcha / invalid credentials can still fail after navigation succeeds.